## Schedule and Gantt
Project Schedule and Gantt Chart
PROJECT TITLE |  | Relocation of Toyota Motor Company from California to Texas |  |  |  |  | PROJECT NAME | [6 empty] | Toyota Motor Company Reloaction
PROJECT MANAGER |  | Vishesh Goel |  |  |  |  | DATE | [6 empty] | 2009-01-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | 2009 | [11 empty] | 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014
[7 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Discussion and Approval |  | 2009-01-01 | 2009-04-30 | 119 | 100% | bar: Q1 1 to Q2 4
1.1 | Board Approval | Executive Board | 2009-01-01 | 2009-04-30 | 119 | 100% | bar: Q1 1 to Q2 4
2 | Planning |  | 2009-05-01 | 2010-05-31 | 390 | 100%
2.1 | Budget Planning | Financial Manager | 2009-05-01 | 2009-10-31 | 180 | 100% | bar: Q2 5 to Q4 10
2.2 | Consultation and Location Assessment | Project Head | 2009-05-01 | 2010-01-31 | 270 | 100% | bar: Q2 5 to Q1 1
2.3 | Site Approval | Executive Board and Stakeholders | 2010-01-31 | 2010-05-31 | 120 | 100% | bar: Q1 1 to Q2 5
3 | Layout and Initial Setup |  | 2010-01-01 | 2011-03-31 | 450 | 100%
3.1 | Contractor Hiring | Project Manager | 2010-01-01 | 2010-04-30 | 119 | 100% | bar: Q1 1 to Q2 4
3.2 | Architectural Layout | Senior Architect | 2010-05-01 | 2010-09-30 | 149 | 100% | bar: Q2 5 to Q3 9
3.3 | Design and Floor Plan | Design Team | 2010-08-01 | 2010-11-30 | 119 | 100% | bar: Q3 8 to Q4 11
3.4 | Interior Setup Design | Design Team | 2010-09-01 | 2011-01-31 | 150 | 100% | bar: Q3 9 to Q1 1
3.5 | Landscape Design | Senior Designer | 2011-02-01 | 2011-03-31 | 60 | 100% | bar: Q1 2 to Q1 3
4 | Construction |  | 2011-04-01 | 2013-03-31 | 720 | 75%
4.1 | Leveling and excavation of land | Contractor | 2011-04-01 | 2011-06-30 | 89 | 100% | bar: Q2 4 to Q2 6
4.2 | Developing the structure | Project Manager | 2011-07-01 | 2012-07-31 | 390 | 100% | bar: Q3 7 to Q3 7
4.3 | Painting and Flooring | Contractor | 2012-04-01 | 2012-09-30 | 179 | 100% | bar: Q2 4 to Q3 9
4.4 | Installation of wires and networks | IT Head | 2012-10-01 | 2012-12-31 | 90 | 100% | bar: Q4 10 to Q4 12
4.5 | Installation of security components | Functional Safety Manager | 2013-01-01 | 2013-02-28 | 57 | 50% | bar: Q1 1
4.6 | Reviews and Rectification | Project Head | 2013-02-01 | 2013-03-31 | 60 | 0%
5 | Shifting |  | 2013-04-01 | 2013-12-31 | 270 | 0%
5.1 | Contractor Hiring | Project Manager | 2013-04-01 | 2013-05-31 | 60 | 0%
5.2 | Transportation of goods | Contractor | 2013-06-01 | 2013-10-31 | 150 | 0%
5.3 | Cushion Time for any unforeseen event | Project Manager | 2013-11-01 | 2013-12-31 | 60 | 0%
6 | Security and Review |  | 2014-01-01 | 2014-05-31 | 150 | 0%
6.1 | Ensuring security measures after the shift | Project Head | 2014-01-01 | 2014-03-31 | 90 | 0%
6.2 | Inspecting the new site | Executive Board | 2014-04-01 | 2014-05-31 | 60 | 0%
Project Progress
YOU CAN ADD MORE OR TAKE OUT LINES WITHIN YOUR SCHEDULE TO FIT YOUR PROJECT. THIS IS ONLY A TEMPLATE.