## Risks
No. | Status | Risk | Impact | Prob'y | Impact Description | Submitted By | Date Identified | Status, Mitigation Strategy | Owner | Key Signs | Risk Index
ID | Open Closed | What is the risk event (or non-event)? | Low Medium High | Low Medium High | What is the effect if the risk occurs? | Person | Date | What is being done now and how is it progressing? What are the timescales for current actions? What would be done if the risk occurred? PREVENT / REDUCE / TRANSFER / CONTINGENCY / ACCEPT | Person | What are the early indicators? | Calculation based on Probability and Impact
R1 | Closed | Inability to provide a secure environment for the data | High | High | The legal holdings and sensitive information of the company are something with which one cannot compromise. | Engineer | 2014-02-20 | Ensuring the cyber security team throughout the process and providing them with sufficient access and control to ensure a robust outcome. | IT Head | Data or any information is the biggest thing for any company with which, they might not want to compromise thus ensuring proper measures is a must | 9
R2 | Closed | Ineffective task handling among the employees | Med | Low | Due to the shift, the tasks may be presumed to have been handled by someone else thus resulting in management chaos. | Project Management Team | 2014-04-14 | Streamlining the entire process and setting up a small team which will ensure that there are no voids left in shifting or switching the task. | Project Manager | This is a common issue arising within teams and with experience, one knows that these issues may come up in such a big move | 2
R3 | Closed | Lack of effective communication and misinterpretations related to the shift | Med | Low | Keeping the employees and the members on board updated about the progress is a great deterministic factor without which the shifting conversion ratio may drop down drastically. | Stakeholders | 2014-03-15 | The board and higher authority ensure that the employees and all the key members are kept well aware of what is going on within the company. | Stakeholders | Uncertainty about the shifting details and constant emails for clarification about the same | 2
R4 | Open | Risks from unidentified internal and external costs | Low | Low | Hidden costs could be another factor that may show up while in the process of relocation. There may be no budget assigned for it and could demoralize the team as a whole. | Financial manager | 2014-03-03 | Keeping extra funds which may add on to the resources allocated for any unforeseen activity | Project Manager | Truck drivers possibly go on a strike during the planning phase of the project itself | 1
R5 | Closed | Damage to the reputation of the company due to the shift as a whole | High | Med | Ill-advised moving could be a major stab to the reputation of the company. Sentiments of those directly or indirectly related to the project must be respected. | Senior Management | 2014-01-28 | The senior management informing and updates the public and end product users about the changes being planned by the company which would, in case something goes wrong, not turn the sentiments against the company. | Executive Board | Fearing the talks about the company not caring about its employees or their sentiments | 6
R6 | Closed | Increased taxation in the near future | High | Med | Cheaper availability of land and better tax rates is one of the driving factors for the shift and a possible increase in these could defeat the entire purpose | Financial analyst | 2013-12-02 | The state government and the company could enter a pact for a few years ensuring that a change in them would not affect the company in any manner | Financial Manager | Considering the already hiked prices in many states and new taxation policies being discussed in various parts of the country | 6
R7 | Open | City council delays with the authorization and paperwork | Med | Med | There may be delays from the city council regarding the legal procedures | Project Management Team | 2014-04-15 | Having enough cushion in matters requiring legal support, so that the tasks to follow don't get affected | Public Relations Head | Delays to fix an appointment initially with the city council | 4
1<=Risk Index<=9
9 being the highest risk and 1 being the lowest risk
|  |  | 9 |  |  |  | 1

## Issues
No. | Status | Priority | Issue | Date Identified | Submitted By | Category | Action/Comments | Owner | Assigned To | Target Date
ID | Open Closed | Low Medium High | What is the issue? | Date | Person | Categorization of issue (e.g.., Scope, Budget, Testing) | What is being done now and how is it progressing? What are the timescales for current actions? | Resolution Owner | Person | Target Date
I1 | Open | High | Dissatisfied employees and less than 60% conversion to the new site | 2014-07-04 | Human Relations Team | Planning | Understanding customer needs. Laying focus on increasing the conversion ratio and providing special perks pertaining to health and education for their family | Stake holders and executive board | Executive Board | 2021-09-01
I2 | Open | High | The budget falls out of bounds with an amount of another $200 million | 2014-08-18 | Financial Manager | Budget | Explaining the sponsors about this increased cost and to consider using the extra cushion to ensure cost reduction wherever possible | Project Manager | Sponsors | 2014-09-15
I3 | Open | Med | The city council was unable to provide appropriate assistance due to some unexpected internal issue | 2014-09-01 | Public Relations Executive | Planning | Using the cushion time kept for these unforeseen circumstances. Followup with them to get their assistance on the most crucial tasks remotely and then other tasks could be catered as and when they are available | Project Manager | Public relations team | 2014-09-30
I4 | Open | High | Upgrading technology leads to a compatibility issue which starts resulting in loss of business | 2014-09-17 | Sales analyst | Testing | Immediately calling for the previous versions of the technology as a backup. Overnight setting up of the systems with a staff that is comfortable with the technology. Cloud keeps the technology backed up thus, it won't be an issue. | Sales Manager | IT Team | 2014-09-24

## Weights (hidden)
Weight
High | 6
Med | 3
Low | 1
Evaluation
> High | 4
< Low | 1.7
Y
N
| High | 3
| Med | 2
| Low | 1
Open
Closed
Closed -> Issue
1 - High
2 - Med
3 - Low
Open
Closed